## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | User Story dependency | Assignee | Status
1 | 1 | US-01 | As an Big Data Developer, I want to export data from file to MongoDb Database. | MUST HAVE | Not Dependent | 1080262 | 3- Completed
2 | 2 | US-02 | As an Big Data developer I want to add a few more internal certifications to certify employees on growing market demand. | MUST HAVE | Dependent on US-01 | 1080262 | 3- Completed
3 | 3 | US-03 | As a MongoDB developer, I want to generate full month name, quarter of the year from the MongoDB table (Date column) in order to analyze the data with month and quarter format. | MUST HAVE | Dependent on US-01 | 1080262 | 3- Completed
4 | 4 | US-04 | As a MongoDB developer, I want to split the records into two collections based on Certification_Type . | MUST HAVE | Dependent on US-01 | 1080262 | 3- Completed
5 | 5 | US-05 | As a py dev I want to combine csv and flat file. | MUST HAVE | Not Dependent | 1080262 | 3- Completed
6 | 6 | US-06 | As a Python programmer, I want to rename entire data certification category “Splunk” as “Big Data” | MUST HAVE | Dependent on US-05 | 1080262 | 3- Completed
7 | 7 | US-07 | As a Python programmer, I need to create a new attribute “Certification_code” | MUST HAVE | Dependent on US-05 | 1080262 | 3- Completed
8 | 8 | US-08 | Using PowerBI, replace the value in marks | MUST HAVE | Dependent on US-01 | 1080262 | 3- Completed
9 | 9 | US-09 | Using PowerBI generate column headers for the “Certification_details.csv” data | MUST HAVE | Dependent on US-01 | 1080262 | 3- Completed
10 | 10 | US-10 | Import transformed data into PowerBI | MUST HAVE | Dependent on US-01 | 1080262 | 3- Completed
11 | 11 | US-11 | As a certification creator, I want to visualize how many people have attended each certification so that the employee performance under the organization can be observed. | MUST HAVE | Dependent on US-10 | 1080262 | 3- Completed
12 | 12 | US-12 | As a course creator, I want to view the average score scored by all the employees in each certification so that the level of certification can be examined. | MUST HAVE | Dependent on US-10 | 1080262 | 3- Completed
13 | 13 | US-13 | As a unit head, I want to view the unit [EmpPucode] wise employee performance in the certifications | MUST HAVE | Dependent on US-10 | 1080262 | 3- Completed
14 | 14 | US-14 | As a quality head, I want to view the certification type, technology type wise performance analysis of the employees in order to understand the utilization of corporate certification | MUST HAVE | Dependent on US-10 | 1080262 | 3- Completed
15 | 15 | US-15 | As an assessment head, I want to view the year wise number of certifications conducted. | MUST HAVE | Dependent on US-11 | 1080262 | 3- Completed
16 | 16 | US-16 | As an assessment head, I want to view the Onsite and Offshore Total Results | SHOULD HAVE | Dependent on US-10 | 1080262 | 3- Completed
17 | 17 | US-17 | As an assessment head, I want to view the Top 10 marks scored by the employees | SHOULD HAVE | Dependent on US-10 | 1080262 | 3- Completed

## Sprint Backlog
User Story # | Description | Story points | Tasks | Effort Estimation in Hours
US 01 | Data import from CSV to MongoDB | 1 | Import Data | 1
US 02 | Add Data to Database | 2 | Insertion of Data | 1
US-03 | Generate full month Name and Quarter | 2 | Generate new columns | 2
US-04 | Splitting the records into two type | 2 | Split the data in two collections | 2
US-05 | Combine two files in python | 1 | Combining two files using pytho | 2
US-06 | Rename entire data 'Splunk' to 'Big Data' | 1 | Renaming data inside the collection | 2
US-07 | Create new attriubute using python | 2 | Creating new coloumn in excel sheet | 1
US-08 | Replace the values using PowerBI | 2 | Replacing 0 with null | 1
US-09 | Generate Column headers in PowerBI | 1 | Geneate Column Header | 1
US-10 | Import Transformed data into PowerBI | 1 | Importing data | 1
US-11 | Visualize how many people have attended each certification | 1 | Visualizing data | 0.5
US-12 | View the average score scored by all the employees in each certification so that the level of certification can be examined. | 1 | Visualizing data | 0.5
US-13 | View the unit [EmpPucode] wise employee performance in the certifications | 1 | Visualizing data | 0.5
US-14 | View the technology wise performance | 1 | Visualizing data | 0.5
US-15 | View the year wise number of certifications conducted. | 1 | Visualizing data | 1
US-16 | View the onsite offshore total results | 1 | Visualizing data | 1
US-17 | View the Top 10 marks scored by the employees. | 1 | Visualizing data | 1

## StandUp Meeting
Sprint | US ID | Day | Points Discussed | Impediments | Action Taken
1 | US-01 | 1 | Learning about mongodbimport. | 1.Lex file provided was not opening. 2.MongoDB verion not working. | Reported to mentor.
1 | US-03 | 1 | Learned about toDate() in python. | toDate() was resulting in error | Corrected the syntax.
1 | US-02 | 2 | Learned about generating new raw data. | Problem in generating relavant bulk data. | Reported to mentor.
1 | US-04 | 2 | Learned about creating path. | Shared path not working. | Got the content stored on shared path from mentor.
1 | US-07 | 3 | Learned how to retrieve JSON file | Problem in retrieving json file from Mongo database | Got help from colleagues and mentor.
1 | US-10 | 3 | Learned how to import JSON file in PowerBI | Importing json file into PowerBI
1 | US-11 | 4 | Understood the Problem Statement. | Understanding the requirement of the question | Asked Colleuges.
1 | US-12 | 4 | Understood the Problem Statement. | Understanding the requirement of the question | Asked the mentor.
1 | US-16,17 | 5 | Discussed on various point of User Stories. | Problem in understanding the differnt ways in which we can think of User Stories | Asked Colleuges.
1 | US-08 | 5 | Learned about replacing values. | Problem in replacing value of 0 to null | Reported to mentor

## Burndown chart
Backlog | 0 |  | Days | 0 | 1 | 2 | 3 | 4
In Progress | 0 |  | Actual Burndown | 24 | 16 | 10 | 8 | 0
Done | 7 |  | Ideal Burndown | 24 | 18 | 12 | 6 | 0
Feature | Priority | Estimated Hour | Status | Day 1 | Day 2 | Day 3 | Day 4
DataGathering | 2 -high | 3 | Done | 3 | 0 | 0 | 0
Cleansing using mongodb | 2 -high | 3 | Done | 3 | 0 | 0 | 0
Transformation using mongodb | 2 -high | 3 | Done | 0 | 3 | 0 | 0
Python Cleansing | 2 -high | 3 | Done | 0 | 3 | 0 | 0
Python-transformation | 2 -high | 4 | Done | 0 | 0 | 3 | 1
Power Bi cleansing | 2 -high | 3 | Done | 0 | 0 | 2 | 1
PowerBi-visualiations | 2 -high | 5 | Done | 0 | 0 | 1 | 4
Agile Burndown